## Slide 1: Team 63: AWG Bi-Weekly Update 2 Leandro Bracho, Nick Joseph, Oscar Medrano, Robin Smithson Sponsor: Dr. John Lusher TA: Zhewen Hu
Notes: Intro should take 30 seconds

## Slide 2: Project Summary
Problem Statement:
  Test validation is a vital step in the design and fabrication of circuit boards for any project in the realm of electrical engineering.
  Typical AWGs can be large and unintuitive
Solution Proposal:
  Create a mobile user interface for the AWG
  Bluetooth connection
  Voltage range of +/- 10 V
  Frequency between 1 Hz – 20 kHz
  Maximum of 65,535 data points
  Allow hand drawn waveforms
Notes: (30 seconds)
Robin

## Slide 3: Project/Subsystem Overview
Diagram showing subsystems – with labels showing subsystem owners
Leandro Bracho | Robin Smithson | Nick Joseph | Oscar Medrano
Android Application | Microcontroller | FPGA | DAC
Notes: (45 seconds)
Robin

## Slide 4: Project Timeline
Update PCBs from feedback from last semester (completed 1/29) | Revalidate & Assess Subsystems (completed 2/5) | Order New PCBs (to complete by 2/16) | Integration of Subsystems (to complete by 2/29) | 3D Print Housing & Installation (to complete by 3/25) | Test & Validation (to complete by 4/22) | Demo and Report (to complete by 4/29)
Notes: (30 seconds) Leandro
-- Save discussion for subsystem update
-- Save detail for execution plan & validation plan status

## Slide 5: Android Application Leandro Bracho
Accomplishments since Update 1 24 hrs of effort | Ongoing progress/problems and plans until the next presentation
Enable Device Discovery Consistent Pairing Connection to MCU | Transfer Data to MCU Improve Bluetooth GUI
Notes: ** Leandro ** (45 Seconds)
For 2nd review should all be in the context of your integration plans! For example:
“Completed X-function in preparation for integrating with Y-subsystem”
“Tested integrated motor controllers with MCU by verifying full range of motion on all 6 joints with no load and 0.5kg load”
“On-going integration of motor control system with MCU”
“By next review will integrate with android app”

## Slide 6: Android Application Leandro Bracho
Bluetooth Scan
Connection Attempt
Android Studio Log Output
Notes: ** Leandro ** (45 Seconds)
Interesting figure related to your subsystem progress ---
Best to show:
Results from prep for integration => integration => test of integrated subsystems

## Slide 7: MCU Robin Smithson
Accomplishments since Update 1 15 hrs of effort | Ongoing progress/problems and plans until the next presentation
Pairing & Connection with Android app achieved App is client, MCU is server PCB Reviewed | Import data from app to MCU Program to export data to FPGA Implement mounting holes & order PCB Unable to program Bluetooth connection on PCB from 403 (using devkit)
Notes: (45 seconds)

## Slide 8: MCU Robin Smithson
Bluetooth Classic Pairing & Connection Code
Notes: (45 seconds)
Interesting figure related to your subsystem progress ---
Best to show:
Results from prep for integration => integration => test of integrated subsystems

## Slide 9: MCU Robin Smithson
Bluetooth Classic Pairing & Connection Code Cont’d
Output
Notes: (45 seconds)
Interesting figure related to your subsystem progress ---
Best to show:
Results from prep for integration => integration => test of integrated subsystems

## Slide 10: FPGA Nick Joseph
Accomplishments since Update 1 12 hrs of effort | Ongoing progress/problems and plans until the next presentation
Finished updating the schematic Most of the PCB is wired | PCB design will be finished by Friday. Have PCB entirely soldered Begin testing connections with the MCU and the DAC

## Slide 11: FPGA Nick Joseph
Circuit Schematics

## Slide 12: FPGA Nick Joseph
PCB Design

## Slide 13: DAC Circuitry Oscar Medrano
Accomplishments since Update 1 5 hrs of effort | Ongoing progress/problems and plans until the next presentation
Have the connectors that will be used to integrate with the FPGA subsystem | Need to make the connector footprint. Routing the PCB Ordering PCB Solder Components Testing PCB

## Slide 14: DAC Circuitry Oscar Medrano
Circuit Schematic

## Slide 15: Power System Oscar Medrano
Accomplishments since Update 1 8 hrs of effort | Ongoing progress/problems and plans until the next presentation
All DC-DC converters have been selected. | Order parts (DC-DC Converters, Capacitors, and Inductors) Designed for the wrong AC adapter

## Slide 16: Execution Plan
 | Jan-22 | Jan-29 | Feb-5 | Feb-12 | Feb-19 | Feb-26 | Mar-4 | Mar-11 | Mar-18 | Mar-25 | Apr-1 | Apr-8 | Apr-15 | Apr-22 | Apr-29 |  |  | 
Andriod Application |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Assess Current Application Status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Not Started | 
Improve Bluetooth Scan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | In Progress | 
Pair & Connect Via Bluetooth |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Completed | 
Transfer Data Via Bluetooth |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Behind Schedule | 
UI Improvements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Microcontroller |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Edit MCU Schematic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Program Bluetooth Connection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Import Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Export Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FPGA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Redesign FPGA board |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Solder New Board |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Test System |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
First Integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Fixing Integration Issues |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
DAC & Power System |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Schematic Design (DAC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Schematic Design (Power Sys) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Order New Parts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Solder Boards |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Test DAC System |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Test Power System |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Jan-22 | Jan-29 | Feb-5 | Feb-12 | Feb-19 | Feb-26 | Mar-4 | Mar-11 | Mar-18 | Mar-25 | Apr-1 | Apr-8 | Apr-15 | Apr-22 | Apr-29 |  |  | 
Project Introduction Presentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Project Update (1) Presentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Project Update (2) Presentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Project Update (3) Presentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Project Update (4) Presentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final Presentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Project Demo |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Power System Designed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
App and MCU Connection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Complete PCB Schematic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final PCBs Ordered |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Parts Still Needed Ordered |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final PCBs Soldered |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Debugging and Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final System Adjustments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Notes: Michelle

## Slide 17: Validation Plan
Notes: Michelle

## Slide 18: Validation Plan
Notes: Michelle

## Slide 19
Thank you